## Stakeholders
Name / Role | Interest in project | Power (1-5) | Interest (1-5) | Engagement approach | Key concern | Communication method
Clinic manager (Sponsor) | Wants fewer no-shows, fuller diary | 5 | 5 | Manage closely | Cost, staff workload | Weekly 30-min check-in
Front-desk receptionists | Run the current manual process | 2 | 5 | Keep informed & consulted | Job changes, extra work | Walkthrough + feedback form at UAT
Patients | Want instant, certain booking | 2 | 4 | Consult (survey + beta) | Ease of use, privacy | In-app survey; beta group
Product Owner | Accountable for delivery | 4 | 4 | Manage closely | Scope creep, timeline | Daily stand-up
Engineering lead | Feasibility & NFRs | 3 | 3 | Keep satisfied | Unclear requirements | Sprint planning + Slack
Compliance advisor (PDPA) | Data protection | 3 | 2 | Keep informed | Unlawful data use | Review at Sprint 1

## Requirements
Req ID | Type | Requirement statement | Source | MoSCoW | Status | Linked story ID | Rationale / business value
BR-001 | Business | Reduce no-show rate from 18% to <=10% within 6 months of go-live. | Clinic manager | Must | Approved | US-001, US-003, US-004, US-009 | Empty slots are lost revenue
BR-002 | Business | Cut front-desk time spent on confirmations/reminders from ~2h/day to <=20 min/day per clinic. | Process analysis | Must | Approved | US-001, US-007 | Receptionists redeployed to patients
FR-001 | Functional | The system shall automatically confirm a booking within 60 seconds when the requested slot is free. | Process map gap #1 | Must | Approved | US-001, US-002 | Removes 24h uncertainty; kills confirmation phone call
FR-002 | Functional | The system shall let a patient reschedule or cancel a confirmed booking in the web app. | Patient interview; gap #3 | Must | Approved | US-003, US-004 | ~30% abandon phone rescheduling -> become no-shows
FR-003 | Functional | The system shall notify the clinic in real time (<5s) when a booking is rescheduled or cancelled. | Receptionist interview | Must | Approved | US-007, US-008 | Clinics plan their day around real schedule
FR-004 | Functional | The system shall release cancelled slots to a waitlist and offer them by SMS in order of request, holding 15 min. | PO decision (mock notes) | Should | Approved | US-006 | Recovers slot value same-day
FR-005 | Functional | The system shall flag cancellations made less than 2 hours before appointment time. | Mock meeting decision | Should | Approved | US-005 | Clinic may still call the patient
FR-006 | Functional | The system shall show clinic address, date/time and prep notes on the confirmation. | Patient interview | Must | Approved | US-002 | Fewer wrong-arrival no-shows
NFR-001 | Non-functional | Confirmation and reschedule endpoints shall respond <2s at p95 under 20 bookings/min. | Engineering lead | Must | Approved | US-011 | UX expectation at 14-clinic load
NFR-002 | Non-functional | Personal data shall be encrypted in transit (TLS 1.2+) and at rest per PDPA. | Compliance constraint | Must | Approved | US-010, US-014 | Legal compliance and trust
NFR-003 | Non-functional | Booking, reschedule and cancel flows shall meet WCAG 2.1 AA. | Product standard | Should | Approved | US-012 | Accessibility for older patients
NFR-004 | Non-functional | All booking events shall be audit-logged with actor, timestamp and before/after state. | Ops requirement | Must | Approved | US-010 | Dispute handling and KPI source

## Backlog
Story ID | Epic | User story (As a / I want / So that) | Acceptance criteria (Given/When/Then) | Points | Priority | Sprint | Status
US-001 | Booking | As a patient, I want instant confirmation when I book a free slot so that I know it is secured. | Given a free slot and valid details, when I tap Confirm, then status becomes CONFIRMED with details shown in <60s. | 5 | High | Sprint 1 | Done
US-002 | Booking | As a patient, I want address and prep instructions in the confirmation so that I arrive prepared. | Given a confirmed booking, when I open it, then I see clinic address, date/time and prep notes. | 2 | High | Sprint 1 | Done
US-003 | Reschedule | As a patient, I want to reschedule in the app so that I don't have to phone the clinic. | Given a booking >2h away, when I pick a new free slot and confirm, then the old slot is released and the new one CONFIRMED. | 8 | High | Sprint 2 | Done
US-004 | Reschedule | As a patient, I want to cancel in the app so the clinic isn't waiting for me. | Given a confirmed booking, when I tap Cancel and confirm, then status becomes CANCELLED and clinic is notified <5s. | 5 | High | Sprint 2 | Done
US-005 | Reschedule | As a patient, I want a warning when changing inside 2 hours so I know the clinic may contact me. | Given a booking starting in <2h, when I attempt change, then a warning shows and the action is flagged to the clinic. | 3 | Medium | Sprint 3 | Done
US-006 | Waitlist | As a waitlisted patient, I want released slots offered by SMS so I can book earlier. | Given a released slot and I am first in line, when the offer is sent, then I have a 15-min hold link; on expiry it passes to the next patient. | 8 | Medium | Sprint 3 | Done
US-007 | Clinic | As front-desk staff, I want real-time notifications so I don't watch the panel all day. | Given any change at my clinic, when it occurs, then badge and event list update <5s. | 5 | High | Sprint 1 | Done
US-008 | Clinic | As front-desk staff, I want today's exceptions in one list so I only make necessary calls. | Given I filter to today, then late-cancels and failed offers appear sorted by time with phone number. | 5 | Medium | Sprint 3 | Done
US-009 | Clinic | As a clinic manager, I want a no-show KPI report so I can measure improvement. | Given month-end, when I open Reports, then no-show rate, reschedule rate and auto-confirm % show vs baseline, exportable to CSV. | 5 | Medium | Sprint 3 | Done
US-010 | Platform | As the product owner, I want all events audit-logged so disputes can be resolved. | Given any booking event, when it happens, then an audit record with actor, timestamp, before/after is written. | 3 | High | Sprint 1 | Done
US-011 | Platform | As the platform, I must respond fast at peak so patients don't abandon. | Given 20 bookings/min, when p95 latency is measured, then confirmation/reschedule endpoints respond <2s. | 5 | High | Sprint 2 | Done
US-012 | Platform | As a patient with a disability, I want accessible flows so I can book independently. | Given WCAG 2.1 AA audit, when booking/reschedule/cancel are checked, then contrast and keyboard navigation pass. | 3 | Medium | Sprint 3 | Done

## UAT
Test ID | Req ID | Scenario | Steps | Expected result | Actual result | Status | Severity
UAT-001 | FR-001 | Auto-confirm free slot | 1. Open booking 2. Choose free slot 3. Confirm | CONFIRMED <60s with details shown | As expected | Pass
UAT-002 | FR-001 | Slot taken mid-booking (negative) | Two users book last slot concurrently | Second user told unavailable, shown alternatives | As expected | Pass
UAT-003 | FR-001 | Network timeout on confirm (negative) | Kill connection at confirm | No duplicate booking; recoverable state; message shown | Duplicate pending record created -> fixed (idempotent confirm) -> retest pass | Pass
UAT-004 | FR-002 | Reschedule >2h before | 1. Open booking 2. Pick new free slot 3. Confirm | Old slot released; new CONFIRMED; details updated | As expected | Pass
UAT-005 | FR-002 | Reschedule to invalid slot (negative) | Attempt past/fully-booked slot | Slot not selectable; clear message | As expected | Pass
UAT-006 | FR-005 | Reschedule <2h before (boundary) | Reschedule a booking 90 min away | Warning shown; action completes, flagged to clinic | As expected | Pass
UAT-007 | FR-002 | Cancel confirmed booking | 1. Open booking 2. Cancel 3. Confirm dialog | Status CANCELLED; clinic notified <5s | As expected | Pass
UAT-008 | FR-002 | Double-tap cancel (idempotency, negative) | Tap Cancel twice rapidly | Single CANCELLED event; one notification | Duplicate SMS queued -> fixed (debounce) -> retest pass | Pass
UAT-009 | FR-003 | Clinic sees change in real time | Patient reschedules; clinic watches panel | Badge + event list update <5s | As expected | Pass
UAT-010 | FR-003 | Exceptions list sorted | Create late-cancel + failed offer | Both in today's exceptions, sorted by time, with phone | As expected | Pass
UAT-011 | FR-004 | Waitlist offer within 15 min | Cancel slot with waitlisted patient | First patient receives SMS with 15-min hold link | As expected | Pass
UAT-012 | FR-004 | Offer expiry routes to next patient (negative) | Ignore SMS >15 min | Slot passes to next waitlist entry; first patient notified politely | Slot released to public booking -> fixed (routes to next waitlist patient) -> retest pass | Pass
UAT-013 | NFR-001 | p95 latency at 25 bookings/min | Load test on staging | <2s at p95 | 1.4s at p95 | Pass
UAT-014 | NFR-002 | PDPA encryption check | Review TLS config, storage, sample logs | TLS 1.2+, at-rest encryption, no phone numbers in logs | As expected | Pass
UAT-015 | NFR-004 | Audit trail completeness | Perform book -> reschedule -> cancel | Audit entry for each event with actor and before/after | As expected | Pass
UAT-016 | FR-006 | Confirmation shows prep notes | Clinic adds note; patient views confirmation | Address, date/time, prep notes visible | As expected | Pass
UAT-017 | NFR-003 | Keyboard-only reschedule (accessibility) | Complete flow using keyboard only | Full flow completable; visible focus; contrast AA | Focus ring missing on date strip -> fixed -> retest pass | Pass
UAT-018 | BR-001 | KPI report reconciles to event log | Generate month-end report | No-show rate matches event log within 0.5% | 0.1% difference | Pass
UAT-003a | FR-001 | Retest: timeout duplicate | Repeat UAT-003 after fix | No duplicate pending record | As expected | Pass
UAT-012a | FR-004 | Retest: waitlist expiry routing | Repeat UAT-012 after fix | Routes to next waitlist patient | As expected | Pass
UAT-019 | BR-002 | Front-desk time on confirmations reduced | Time-log sample: exceptions workflow vs manual phone process | Exceptions handled from dashboard; manual confirmations <=20 min/day | As expected | Pass

## RAID
ID | Type | Description | Impact (H/M/L) | Likelihood (H/M/L) | Owner | Mitigation / action | Status
R-001 | Risk | Patients distrust or resist app changes | M | M | Project lead | Beta with 2 clinics; keep phone fallback 60 days | Open
R-002 | Risk | SMS gateway pricing changes erode ROI | M | M | Product owner | Lock 12-month rate in contract; quarterly review | Open
A-001 | Assumption | Clinic volume ~100 bookings/day/clinic | - | - | BA | Validate against admin stats in week 1 of build | Open
A-002 | Assumption | 50% of recovered slots translate to kept revenue | - | - | BA | Track rebooking behaviour in KPI report | Open
I-001 | Issue | SMS gateway sandbox keys not received | H | M | Product owner | Chase vendor; fallback email for beta (used in S2) | Closed
I-002 | Issue | Waitlist expiry defect found in UAT (Sev-2) | H | - | Engineering lead | Fixed and retested (UAT-012a) | Closed
D-001 | Dependency | PDPA review of data flows | M | L | BA | Completed Sprint 1; sign-off on file | Closed
D-002 | Dependency | Clinic beta users available for UAT | M | M | Clinic manager | 2 clinics confirmed; walkthrough done | Closed

## Summary
Project Summary — QuickKlinik Reschedule Release (independent case study)
REQUIREMENTS
Total requirements
Must-have
Requirements linked to a story
Story coverage %
Requirements with at least one UAT test
Test coverage %
BACKLOG
Total story points
Points done
Progress %
UAT
Tests run
Pass rate
Open defects (Fail)
RAID
Open risks / issues